## Fee Proposal
ATT: | Bob Pan |  |  |  |  | Reference: | 401000AH
| Archizone |  |  |  |  | Date: | 2024-01-22
| Suite26, 105 Longueville Road, Lane Cove, NSW 2066 |  |  |  |  | Revision: | 1
Dear Bob,
Re: The Char Rotisserie, 249 King Street, Newtown
Thank you for giving us the opportunity to submit this fee proposal for our Mechanical Service, Kitchen Ventilation for the above project.
At PCE we are proud of our tailored solutions and prompt service. Our typical design turn-around period is 2-3 business days for a standard restaurant/office fitout project. Please refer to the following details on our proposed project stage, service scope, and the required key design basis information. Once the required information is provided, we endeavour to deliver quality, accurate and timely design package.
| Fee proposal stage |  |  |  |  | 1-2 | business day
• | Identify scope of work, confirm what items are needed
• | Receive architectural/interior drawings, project specific requirements (provide by the client)
• | Receive site photos or other site condition information (provide by the client)
| Pre-design information collection |  |  |  |  | 2-4 | business day
• | Receive base building drawings detailing information of service provision.
• | Confirm specific requirements from the base building and other stakeholders
• | Perform site visit (if included), obtain site photos(inside and outside of the tenancy, shopfront, roof)
| Documentation and issue |  |  |  |  | 1-2 | business day
• | Discuss with architect to finalize details including design coordination
• | Receive final architectural/interior design drawings (provide by the architect)
• | Note: We require full invoice to be paid before issuing full set of documentation
Post-issue service
• | Answer RFIs
• | Maximum 2 free drawing amendments allowed
• | Note: We also offer optional installation service. Please contact us for further discussion.
Yours faithfully,
Felix Ye
Director, MEP
M: 0426 076 689
E: felix@pcen.com.au
1 | GENERAL DESCRIPTION OF WORK
• | Describe the engineering systems by means of drawings.
• | Carry out detailed calculations.
• | Pre-empt and address constructability issues within documents where possible.
• | Refer details for client and authority approval where appropriate.
• | Co-ordination checks with other services.
2 | SPECIFIC SCOPE OF WORK AND EXCLUSION
2.1 | Mechanical Service-Extent
• | Map out existing mechanical components
• | Commercial kitchen exhaust and makeup air system design;
• | Air conditioning design to the tenancy area as required;
• | Grilles coordination with RCP
• | Natural ventilation design
• | Other ventilation as required to AS 1668.2
• | Coordination with stakeholder and other services
• | 1 off site visit
2.2 | Mechanical Service-Clarifications
• | Assessment of compliance with environmental noise regulations
• | Preparation of Performance Solutions
• | Odour management report, please liaise with us cost of the report from us
2.3 | Mechanical Service-Deliverables
• | Full set of mechanical drawings in PDF format
• | Mechanical design certificate
• | Equipment selection
3 | PCE Capabilities
3.1 | Expertise
We specialise in providing tailored engineering solutions with a strong focus on high quality, close collaboration, and exceptional customer service. All our consultants are qualified and knowledgeable professionals. We have extensive experience in not only Mechanical, But also Electrical and Hydraulic services.
3.2 | Qualification
Our team of engineers are highly experienced and fully qualified. Our qualifications relating to this project include:
• | MIEAust, M.AIRAH, CPEng, NER, RPEQ
• | BDC C9 Mechanical Certifier
• | DBP Class 2 building Design Practitioner
3.3 | Project Experience
We have enormous experience in this area. Some of our previous works are:
• | KFC (International fast food chain), Baulkham Hills, Rhodes, Gregory Hills, North Sydney, St Ives
• | Hai Di Lao, Darlin Harbour and Chatswood (international Premium Hot-Pot chain )
• | Hanok Korean (Charcoal Korean charcoal BBQ), Dickson ACT, Miranda, Wollongong, Phillip, Kotara, Campbell Town, Tuggerah, Wagga Wagga
• | The Grounds of Alexandria (stylish café, bar, restaurant, garden and event hub)
• | Leaf Café (award winning coffee, coffee franchises), Emerton, Rhodes, Marsden Park, Westmead, The Ponds, Pennant Hills, Success WA
• | Meet Fresh (contemporary exquisite desserts), Chatswood, Eastwood, Burwood, Haymarket, Waterloo
• | Stacked (Fast food chain) North Sydney, Mascot, Sydney, Westfield Sydney, Penrith
• | WE Kitchens (modern central commercial kitchen hire services)
• | Kagoshima Master, Ultimo and Crowns Nest (authentic Wagyu Yakiniku restaurant)
• | Mamaks Village, Darling Harbour and Martin Place (authentic Malaysian cuisine)
3.4 | Project Resources
Our key personnel proposed for this project are as follows:
| Director/Mechanical Engineer |  |  | - Felix Ye (ME CPEng NER RPEQ DBP)
We confirm that we will not engage any sub-consultants.
4 | INSURANCE DETAILS
We currently hold the following insurances to as required by authorities
| Insurance type |  | Insurer |  | Amount
| Professional indemnity |  | Allianz |  | 10000000
| Public Liability |  | CGU |  | 20000000
Copies of insurance certificate are available upon request.
5 | CONDITIONS OF ENGAGEMENT
We confirm that this will be a direct commission from your firm. You may accept the offer by completing the Signature of Acceptance form at the end of this document, but if you do not, your continued instructions to us will constitute your acceptance of the offer.
6 | FEE
6.1 | Fee Proposal Details
We are pleased to outline below our lump sum fees for the provision of services to be undertaken in accordance with the aforementioned scope of service.
| Services |  |  |  | Total ex.GST | Total in.GST
| Mechanical Service design and documentation |  |  |  | 2500 | 2750
|  | Total |  |  | 2500 | 2750
6.2 | Hourly Rates
We only provide 2 free amendments. Any additional work required beyond the scope defined will be charged at hourly rates. The following rates (GST exclusive) are current to project completion.
| Engineer |  | - | 280 | per hour
| Administration |  | - | 150 | per hour
| Site Visit/Meeting(extra) |  | - | 450 | per 3 hour section inclusive travelling
6.3 | Claiming of Fees
Payment is due within 14 days of the date of invoice.
7 | SIGNATURE AND APPROVAL
Re: The Char Rotisserie, 249 King Street, Newtown
|  | Client |  |  | Engineer
| Company: |  |  |  | Premium Consulting Engineers
| Full Name: |  |  |  | Felix Ye
Director/Mechanical Engineer
NSW Fair Trading C9 Certifier
NSW Fair Trading Professional Engineer
M.E CPEng NER RPEQ
M: 0426 076 689
Signature:
| Date: |  |  |  | 2024-01-22
TERMS AND CONDITIONS
1 | The Consultant shall provide to the Client the consulting services described in the accompanying letter together with such other services as may be agreed from time to time (the "Services").
2 | The Consultant shall provide the Services with such skill, care and diligence as is generally exercised by competent members of the consulting profession performing services of a similar nature, at the time the Services are provided.
3 | The Services will be performed at either or both the site of the project (the "Site") or at other places reasonably required by the Client. Where the locations of the Consultant’s work are not under the Consultant’s control (including the Site), the Client must provide reasonable access to allow the Consultant to fulfil its obligations (including to provide the Services).
4 | The Client shall, at its own cost, as soon as practicable make available to the Consultant all information, documents and other particulars relating to the Client's requirement for the project as is necessary for the Consultant to carry out the services as expressly set out in this Agreement (the "Requirements"). The Consultant is entitled to rely on such information, documents and other particulars as are provided by the Client pursuant to or in connection with this Agreement.
5 | The Client shall pay to the Consultant:
a) the Fee and the Reimbursable Expenses as set out in the accompanying letter together with such other amounts in respect of other services agreed to be provided;
b) reasonable adjustments to the Fee and the Reimbursable Expenses to reflect the additional costs, expenses, liabilities, losses or other amounts incurred or suffered by the Consultant in the performance of the Services and arising out of or in connection with any event or matter beyond the Consultant’s control; and
c) to the extent that amounts payable under this Agreement are not expressed to be GST inclusive, an additional amount for the GST incurred by the Consultant in relation to the supply of the Services ("GST").
6 | The Consultant may claim payment in accordance with the times set out in the accompanying letter or, if no time is set out, monthly in arrears. The Client must pay to the Consultant, without set-off or deduction:
a) the amount payable under this Agreement for the Services provided during the relevant period, within 15 days of the Consultant’s invoice; and
b) the GST payable under this Agreement for the Services provided during the relevant period, within 15 days of receiving a valid tax invoice.
7 | If the Client does not pay the Consultant in accordance with this Agreement then, without prejudice to any other rights or remedies the Consultant may have, interest will be payable from the date of invoice until payment at a rate per annum equal to the Unsecured Personal Overdraft Rate as most recently published by Westpac, plus 1% per annum.
8 | To the maximum extent permitted by law:
a) subject to paragraphs (b), (c) and (d) below, the Consultant’s liability to the Client arising out of or in connection with this Agreement (including the performance or non-performance of the Services), whether under the law of contract, in tort, in equity, under statute or otherwise, shall be limited in aggregate to the amount specified in the accompanying letter or $300,000, if no amount is stated in the letter.
b) the Consultant is not liable to the Client in respect of any indirect, consequential or special losses (including loss of profit, loss of business opportunity and payment of liquidated sums or damages under any other agreement);
c) the Consultant shall be deemed to have been discharged from all liability in respect of the Services whether under contract, in tort, in equity, under statute or otherwise, at the expiration of the period specified in the accompanying letter, or if no date is specified, on the expiration of 3 years from the completion of the Services;
d) if, and to the extent that, any of this clause is void as a result of section 68 of the Trade Practices Act 1974 (Cth), then the Consultant’s liability for a breach of a condition or warranty is limited to:
(i) the supplying of the relevant Services again; or
(ii) the payment of the cost of having the Services supplied again.
9 | Subject to the Client complying with its obligations under the Agreement, the Consultant grants to the Client a non-exclusive, royalty-free and irrevocable licence to use (and allow others to use) any intellectual property (including all drawings, reports, specifications, bills of quantity, calculations and other documents, including "works" as defined in the Copyright Act 1968 (Cth) created or produced by the Consultant) arising out of provision of the Services ("IP Rights") for the purposes of completing the Project. As between the Client and the Consultant, the ownership of the IP Rights vests in the Consultant.
10 | Neither the client nor the Consultant shall disclose to third parties or use for any purpose (other than providing or benefiting from the Services) any information provided by the other unless:
a) required by law;
b) the information is already generally known to the public; or
c) the other consents to the disclosure.
All documentation and materials containing confidential information provided by one party to the other shall be returned upon request.
11 | Any dispute or difference ("Dispute) between the Client and the Consultant may be notified by a party to the other party and the parties shall:
a) firstly meet to negotiate, in good faith, resolution of the Dispute; and
b) secondly, if negotiation fails to achieve a resolution of the Dispute within 5 working days of the notification of the Dispute, attend mediation, administered in accordance with procedures as set out by the Institute of Arbitrators and Mediators Australia, provided that this provision shall not prevent the Consultant from instituting legal action at any time to recover moneys owing by the Client to the Consultant.
12 | The Client may, without prejudice to any other rights or remedies it may have, by written notice served on the Consultant terminate its obligations under this Agreement:
a) if the Consultant is in breach of the terms of the Agreement and the breach has not been remedied within 28 days of a written notice served by the Client on the Consultant specifying the breach and requiring the breach to be remedied; or
b) upon the Client giving the Consultant 60 days' written notice of its intention to do so; or
c) if the Consultant informs the Client that it is insolvent, becomes bankrupt, or becomes subject to any official management, receivership, liquidation, provisional liquidation, voluntary administration, winding up or external administration ("Insolvency Event").
The Consultant may, without prejudice to any other rights or remedies it may have, by notice in writing served on the Client suspend its obligations under this Agreement:
13 | The Consultant may, without prejudice to any other rights or remedies it may have, by notice in writing served on the Client suspend its obligations under this Agreement:
a) immediately by written notice if the Client has failed to pay in accordance with this Agreement; or
b) if the Client is in breach of any of the other terms of the Agreement and the breach has not been remedied within 10 working days (or longer as the Consultant may allow) of a written notice served by the Consultant on the Client specifying the breach and requiring the breach to be remedied.
14 | The Consultant may, without prejudice to any other rights or remedies it may have, terminate its obligations under this Agreement:
a) if the breach referred to in clause 13(a) has not been remedied within 5 days of a written notice served by the Consultant on the Client specifying the breach and requiring the breach to be remedied; or
b) if the Client is in breach of any of the other terms of the Agreement and the breach has not been remedied within 28 days of a written notice served by the Consultant on the Client specifying the breach and requiring the breach to be remedied; or
c) upon the Consultant giving the Client 60 days' written notice of its intention to do so; or
d) if an Insolvency Event occurs in relation to the Client.
15 | If the Consultant considers it appropriate to do so, it may, with the Client's prior approval, which shall not be unreasonably withheld or delayed, engage other consultants to assist the Consultant in specialist areas. The other consultant shall be engaged at the Client's risk, cost and expense, and on its behalf.
16 | Neither party may assign, transfer or sublet any obligations under this Agreement without the written consent of the other. Unless stated in writing to the contrary, no assignment, transfer or subletting shall release the assignor from any obligation under this agreement.
17 | In the interpretation of this Agreement, no rule of construction applies to the disadvantage of one party on the basis that it put forward this Agreement or any part of it.