## 01-Project Info
Project Name: | 30 Kerr Parade, Auburn |  |  | Asana Field information |  |  |  |  | Asana Project template - Residential |  | Service Type |  |  | Project Reference
Shop Name: | 30 KERR PARADE, AUBURN |  |  | Shop name: |  |  |  |  | 1 | Set up project folder, Compile fee proposal | Hydraulic Service |  |  | Group House Reference
Quotation Number: | 207000C |  |  | Apt/Rooms | Apt | Rooms |  |  | 2 | Finalize fee proposal and email to the client | Electrical Service |  | • | Group House | 18 Fisher Ave, Vaucluse (PSEC Project Services)
Project Number: | INV-1 |  |  | Basement/Car Spots: |  |  |  |  | 3 | Fee accepted? Ventilation and AC? Set project No., issue invoice | Fire Service |  | • | Group House | 10 Cecil Street, Paddington (25 rooms, Cracknell & Lonergan Architects Pty Ltd)
Project Type: | Apartment |  |  | Feature/Notes: |  |  |  |  | 4 | Setup drawings, do preliminary cals | Kitchen Ventilation |  | • | Group House | 10 Belinda Place, Mays Hill (27 units, Harrison Group Pty Ltd)
Service Type 1: | Mechanical Service | [7 empty] | 5 | Car park natural ventilation | Mechanical Service |  | • | Group House | 8-10 Gollan Avenue, Oatlands (Jonathan Crutcher)
Service Type 2: | [8 empty] | 6 | Felix to liaise with client for project progress | CFD Service |  | • | Group House | 30 Kerr Parade, Auburn (140 rooms, Zhinar Architects)
Service Type 3: | [8 empty] | 7 | Update background | Mech Review |  | • | Group House | 11 Yarranabbe Road, Darling Point (Tros Architecture Interior)
Service Type 4: | [8 empty] | 8 | Continue for drawings | Installation |  | • | Group House | 1 Hill Street, Wentworthville (Phoenix Building Approvals Pty Ltd)
Service Type 5: | [8 empty] | 9 | PCE INV xxxxxx sent, paid? | Miscellaneous |  | • | Group House | 22 Ramsay Street, Collaroy (Sandy Kong)
Client Full Name: |  |  |  | Client: |  |  |  |  | 10 | Check sketch and send to client |  |  | •
Client Company: | [8 empty] | 11 | [Option] Design Meeting |  |  | •
Client Address: | [8 empty] | 12 | Update arch background |  |  |  |  | <Add extra reference projects>
Client ABN: | [8 empty] | 13 | Update drawings using new arch | Project Type
Contact Number/Email: | [8 empty] | 14 | Equipment Schedule | Restaurant | 41000 |  | Apartment Project reference
[9 empty] | 15 | Update Sketch, check background update | Office | 42000 | • | Apartment | 38 Cudgegong Road, Rouse Hill (Zhinar Architects, 295 Apartments, $200m)
Main Contact Full Name: |  |  |  | Main Contact: |  |  |  |  | 16 | Issue Last invoice xxxxxx sent, Paid? | Commercial | 43000 | • | Apartment | ‘Crownview’, 373 Crown Street, Wollongong (mixed-used twin tower, 149 apartments)
Main Contact Company: |  |  |  | Contact type: |  |  |  |  | 17 | Update mechanical drawing | Group house | 44000 | • | Apartment | ‘Regent’, 58-68 Regent Street, Kogarah (PBD Architects,12-storey, 96 high-end apartments, $80m)
Main Contact Address: | [8 empty] | 18 | Review background update; Update Sketchs | Apartment | 45000 | • | Apartment | ‘Grand Auburn’, 5-7 Northumberland Road, Auburn (Zhinar Architects, mixed-used, 116 apartment, $110m)
Main Contact ABN: | [8 empty] | 19 | Review and Check | Mixed-use complex | 46000 | • | Apartment | 23-27 Schofields Road, Schofields (Binah Construction, 137 Apartments, $100m)
Contact Number/Email: | [8 empty] | 20 | Update toilet exhaust to not discharge in lift shaft, talk to FY before starting | School | 47000 | • | Apartment | 27-33 Ascot Street, Canley Heights (Zhinar Architects, 74 Apartments, $60m)
[9 empty] | 21 | Review and check | Others | 48000 | • | Apartment | 31 Warriewood Road, Warriewood (DKO Architects, 5-storey 104 apartments, $90m)
[13 empty] | • | Apartment | 35-39 Jenkins Road, Carlingford (Blue Sox Developments, 60 Apartments, $45m)
[9 empty] | Asana Project template - CFD |  |  |  | • | Apartment | ‘The Pearson’, 2-6 Pearson Ave, Gordon (Wolski Coppin Architecture, boutique apartment)
[9 empty] | 1 | Set up project folder |  |  | • | Apartment | The Mitchell', 11-15 Mitchell Avenue, Jannali (PBD Architects, 31 featured apartments)
Building Feature | [8 empty] | 2 | Finalize fee proposal and email to the client | Contact Type |  |  |  | <Add extra reference projects>
[9 empty] | 3 | Fee accepted? Ventilation and AC? Set project No., issue invoice | Architect
[9 empty] | 4 | CFD fee proposal to client | Builder |  |  | Mixed-use Complex reference
[9 empty] | 5 | Client meeting | Certifier |  | • | Mixed-use Complex | 8 Dumaresq Street, Campbelltown (tqm Construcion, Mixed-Use with Apartments, $450m)
Level | Other type of room excetp car spots and storage cages | Car Park A |  | Car Park B |  | Car Park C |  |  | 6 | Combined Arch, Setup Sketch Background | Contractor |  | • | Mixed-use Complex | 93 Forest Road, Hurstville (DKO Architects, 4 towers, 550 apartments and commercial/retail)
|  | Car spots | Other | Car spots | Other | Car spots | Other |  | 7 | Sketch | Developer |  | • | Mixed-use Complex | 26 Elizabeth Street, Liverpool (Rothe Lowman Architect, $300m)
[9 empty] | 8 | Review and check | Engineer |  | • | Mixed-use Complex | Grosvenor Place, 225 George Street, Sydney (Sydney Sky Scraper Chiller replacement, $100m)
[9 empty] | 9 | EQUIPMNET schedule | Government |  | • | Mixed-use Complex | 2-4 Cambridge Street, Epping (Zhinar Architects, 83 Mixed-Use Apartments, $90m)
Basement 3 |  | 24 | [6 empty] | 10 | Preliminary sketch sent, feedback? | RDM |  | •
Basement 2 |  | 24 | [6 empty] | 11 | Client meeting | Strata |  | •
Basement 1 |  | 17 | [6 empty] | 12 | Fix & Review updated Mech Sketch | Supplier |  | •
[9 empty] | 13 | Kick off Invoice xxxxxx sent, Paid? | Owner/Tenant |  | •
[9 empty] | 14 | Last invoice, 50% | Others |  | •
Total Car spot |  | 65 |  | 0 |  | 0 |  | 65 | 15 | Setup CFD -To CFD |  |  |  |  | <Add extra reference projects>
Total Others |  |  | 0 |  | 0 |  | 0 | 0 | 16 | Check CFD and send to China， awaiting arch dwg
[9 empty] | 17 | Get CFD from China, check if CFD modelling done?
[9 empty] | 18 | Update sketch to reflect CFD model setting
Level | Other type of room excetp apartments | Block A |  | Block B |  | Block C |  |  | 19 | Review and send draft CFD issue to client
|  | Apt | Comm | Apt | Comm | Apt | Comm |  | 20 | Client feedback? send final report
Total Levels |  | 12 Levels | [6 empty] | 21 | [Option] Design Meeting
Ground |  | 4 | 1 | [5 empty] | 22 | Equipment schedule to elec
Level 9 |  | 13 | [6 empty] | 23 | Check and update
Level 10 |  | 12 | [6 empty] | 24 | Update sketch
Level 11 |  | 12 | [6 empty] | 25 | [Option] Design Meeting
Roof
Total Apt |  | 41 |  | 0 |  | 0 |  | 41
Total Commercial |  |  | 1 |  | 0 |  | 0 | 1 | 27 | Incorporate arch comments on mech sketch
[9 empty] | 28 | [Option] Design Meeting
[9 empty] | 29 | Update Drawings, and CFD SKETCH, to CFD
[9 empty] | 30 | Update Background and overlay
[9 empty] | 31 | Check and review CFD report, send to client
Note: Client information auto-linked to 'Fee Porposal' and 'Invoice' Section.
If the person whom invoice to (ultimate client) is different from the person originally asks for quote, fill Client details with 'invoicing client' but fill the 'Main Contact' with 'quoting client'.

## 02a-Fee Cals
| 0 |  |  |  | 0 | (Y/N)
| Engineering Fee of Build Cost % |  |  |  | 0.4%
Method 1: Design Fee Calculated via building Cost
| No. off or m2 | Average Value | Build Cost | Eng Fee |  |  |  | Mech |  |  | Elec |  |  | Hyd |  |  | Fire
Basement calc by area or, |  | 500 | 0 | 0 |  |  |  | (% of Eng Fee) |  |  | (% of Eng Fee) |  |  | (% of Eng Fee) |  |  | (% of Eng Fee)
by no. of car spots | 65 | 20 | 650000 | 2600
Commercial | 5795 | 3000 | 17385000 | 69540 |  |  |  | 30% |  |  | 30% |  |  | 23% |  |  | 17%
Apartment | 41 | 400000 | 16400000 | 65600
|  |  | Total | 137740 |  |  |  | 41322 |  |  | 41322 |  |  | 31680.2 |  |  | 23415.8
| Project Phases |  | Schematic | 13774 |  |  | 10% | 4132.2 |  | 10% | 4132.2 |  | 10% | 3168.02 |  | 10% | 2341.58
|  |  | Design Development | 61983 |  |  | 45% | 18594.9 |  | 45% | 18594.9 |  | 45% | 14256.09 |  | 45% | 10537.11
|  |  | Documentation | 41322 |  |  | 30% | 12396.6 |  | 30% | 12396.6 |  | 30% | 9504.06 |  | 30% | 7024.74
|  |  | Construction Services | 20661 |  |  | 15% | 6198.3 |  | 15% | 6198.3 |  | 15% | 4752.03 |  | 15% | 3512.37
|  |  |  | 137740 |  |  |  | 41322 |  |  | 41322 |  |  | 31680.2 |  |  | 23415.8
Method 2: Design Fee Calculated via Workload/PCE Statistic Figure
| No. off | Rate | Sum
Design Sketches | 10 | 800 | 8000 |  | Check Figure - $/Apartment | [13 empty] | Check Figure - $/m2 Commercial area
AutoCAD drawings | 8 | 1200 | 9600 |  | Total Apts： | 41 | [12 empty] | Total Areas： | 5795
Design meetings | 4 | 350 | 1400 |  | 80 | 3280 |  | 320 | 13120 |  | 560 | 22960 |  | 800 | 32800 |  | 1100 | 45100 | 2 | 11590
Site visit and defect report | 2 | 800 | 1600 |  | 100 | 4100 |  | 340 | 13940 |  | 580 | 23780 |  | 820 | 33620 |  | 1150 | 47150 | 4 | 23180
Class 2 certification | 2 | 1200 | 2400 |  | 120 | 4920 |  | 360 | 14760 |  | 600 | 24600 |  | 840 | 34440 |  | 1200 | 49200 | 6 | 34770
custum item 1 | 0 | 0 | 0 |  | 140 | 5740 |  | 380 | 15580 |  | 620 | 25420 |  | 860 | 35260 |  | 1250 | 51250 | 8 | 46360
custum item 2 | 0 | 0 | 0 |  | 160 | 6560 |  | 400 | 16400 |  | 640 | 26240 |  | 880 | 36080 |  | 1300 | 53300 | 10 | 57950
custum item 3 | 0 | 0 | 0 |  | 180 | 7380 |  | 420 | 17220 |  | 660 | 27060 |  | 900 | 36900 |  | 1350 | 55350 | 12 | 69540
custum item 4 | 0 | 0 | 0 |  | 200 | 8200 |  | 440 | 18040 |  | 680 | 27880 |  | 920 | 37720 |  | 1400 | 57400 | 14 | 81130
custum item 5 | 0 | 0 | 0 |  | 220 | 9020 |  | 460 | 18860 |  | 700 | 28700 |  | 940 | 38540 |  | 1450 | 59450 | 16 | 92720
[5 empty] | 240 | 9840 |  | 480 | 19680 |  | 720 | 29520 |  | 960 | 39360 |  | 1500 | 61500 | 18 | 104310
|  |  | 23000 |  | 260 | 10660 |  | 500 | 20500 |  | 740 | 30340 |  | 980 | 40180 |  | 1600 | 65600 | 20 | 115900
[5 empty] | 280 | 11480 |  | 520 | 21320 |  | 760 | 31160 |  | 1000 | 41000 |  | 1700 | 69700 | 22 | 127490
[5 empty] | 300 | 12300 |  | 540 | 22140 |  | 780 | 31980 |  | 1050 | 43050 |  | 1800 | 73800 | 24 | 139080
Method 3: Design Fee Calculated as per scope of work
Internal Cost | Drafter | Designer | Principal | Subconsultant | Total |  | Additional Expenses |  | Total |  |  |  | Reference - Price
Calculations | 0 | 45 | 15 | 0 | 60 |  | Travel: $750 x 2 days |  | 1500 |  |  |  |  | Resource | Daily rate |  | Hourly rate
Design Sketches | 30 | 15 | 7.5 | 0 | 52.5 |  | External signoff |  | 2000 |  |  |  |  | Drafter | 80 | /hour | 600 | /day
AutoCAD drawings | 0 | 0 | 0 | 30 | 30 |  | Copy & printing |  | 200 |  |  |  |  | Designer | 120 | /hour | 900 | /day
Design review | 0 | 15 | 15 | 0 | 30 | [8 empty] | Principal | 200 | /hour | 1500 | /day
Design meetings | 0 | 0 | 15 | 0 | 15 | [8 empty] | Subconsultant | 150 | /hour | 1125 | /day
Site visit and defect report | 0 | 0 | 7.5 | 0 | 7.5
Class 2 certification | 0 | 0 | 7.5 | 0 | 7.5
custum item 1 | 0 | 0 | 0 | 0 | 0
custum item 2
| 30 | 75 | 67.5 | 30 | 202.5
| 2400 | 9000 | 13500 | 4500 | 29400 |  |  |  | 3700
|  |  |  | Total Price | 33100
Design Fee for Car Park Ventilation CFD
Project | Carpark Level | CFD Calc Level | No of Carports | Level Factor | Carport Factor | Complex Factor | CFD Cost $
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
Altogeterh | 3 | 3 | 441 | 1.5 | 4.9 | 7.35 | 4000
Spare |  |  |  | 0 | 0 | 0 | 0
INSTRUCTIONS
1. Complex Factor = No. of CFD Calc Level x Carport Factor. Level factor = 1 + 0.25 x extra levels; Carport Factor =No of Carports / 90 Example: Project 106115-178-188 Pennant Street, North Parramatta. No. of carpark level = 1 No. of CFD calculated carpak level =1 No. of Carport = 53 Calculated Result: Level Factor = 1 Carport Factor= 53/90 = 0.59 Complex Factor = 1 x 0.59 = 0.59 CFD Cost = $2000
2. CFD Cost Lookup Table
Scale of Carpark | Calculation Criteria |  |  | CFD Cost $
Extremely Small | Complex Factor ≤0.5 |  |  | 1000
Small | 0.5＜Calculation Complex Factor ≤1 |  |  | 2000
Small-Medium | 1＜Calculation Complex Factor ≤5 |  |  | 3000
Medium | 5＜Calculation Complex Factor ≤10 |  |  | 4000
Medium-Large | 10＜Calculation Complex Factor ≤15 |  |  | 5000
Large | Calculation Complex Factor ＞15 |  |  | 6000
3. Mimium CFD Cost is $1000. (when Complex Factor =0.5 or less)
PROJECT REFERENCES
Project |  | Carpark Level | CFD Calc Level | No of Carports | Level Factor | Carport Factor | Complex Factor | CFD Cost $
012203-9-11 Mary Street, Auburn |  | 4 | 1 | 23 | 1 | 0.25556 | 0.25556 | 1000
103067-10 Cecil Street, Paddington |  | 1 | 1 | 5 | 1 | 0.055556 | 0.055556 | 1000
106115-178-188 Pennant Street, North Parramatta |  | 1 | 1 | 53 | 1 | 0.58889 | 0.58889 | 2000
107144-900 Pacific Highway, Gordon, CFD |  | 3 | 3 | 36 | 1.5 | 0.4 | 0.6 | 2000
112251-A-10 Belinda Place, Mays Hill |  | 2 | 2 | 14 | 1.25 | 0.15556 | 0.19444 | 1000
111241-A-26 Elizabeth Street, Liverpool |  | 5 | 5 | 365 | 2 | 4.0556 | 8.1111 | 4000
111246-A-930 Old Northern Road & 4 Post Office Road, Glenorie |  | 2 | 2 | 212 | 1.25 | 2.3556 | 2.9444 | 3000
111238-A-474 President Avenue, Kirrawee |  | 1 | 1 | 11 | 1 | 0.12222 | 0.12222 | 1000
111000R-18 Todd Street, Merrylands West | [7 empty] | 0
210012-4-6 Uhrig Street, Lidcombe |  | 7 | 7 | 578 | 2.5 | 6.4222 | 16.0556 | 6000
111000P-152 Henry Lawson Avenue, Werrington |  | 2 | 2 | 120 | 1.25 | 1.3333 | 1.6667 | 3000
205082-2-4 Merinda Street and 24-26 Mindarie Street, Lane Cove North |  | 2 | 2 | 90 | 1.25 | 1 | 1.25 | 3000
234-236 Cumberland Road, Auburn-Carpark |  | 2 | 2 | 36 | 1.25 | 0.4 | 0.5 | 1000
87 Willarong Road, Caringbah-Carpark |  | 3 | 3 | 34 | 1.5 | 0.37778 | 0.56667 | 2000
201006-23-27 Schofields Road, Schofields-Simon |  | 2 | 2 | 165 | 1.25 | 1.8333 | 2.2917 | 3000
35-39 Jenkins Road, Carlingford-Carpark |  | 2 | 2 | 106 | 1.25 | 1.1778 | 1.4722 | 3000
20220914 CabraVale Diggers Club, 1 Bartley Street, Canley Vale |  | 2 | 2 | 317 | 1.25 | 3.5222 | 4.4028 | 3000
50-52 Lethbridge Street, Penrith-Carpark Sketch |  | 2 | 2 | 75 | 1.25 | 0.83333 | 1.0417 | 3000

## 02b-Fee Proposal
30 Kerr Parade, Auburn
Mechanical Service Fee Proposal
Prepared for: |  |  |  |  | Prepared by:
Felix Ye
Premium Consulting Engineers
ABN: 36 627 724 029
Suite 802, 299 Sussex Street Sydney 2000
Date:
2023-09-19 | [7 empty] | T: 0426 076 689 E: felix@pcen.com.au
ATT: | [5 empty] | Reference: | 207000C
[6 empty] | Date: | 2023-09-19
[6 empty] | Revision: | 1
Dear ,
RE: 30 Kerr Parade, Auburn
Thank you for giving us the opportunity to submit this fee proposal for our Mechanical Service for the captioned project.
Premium Consulting Engineers provides innovative and best practice engineering solutions with a strong focus on high quality, close collaboration, and exceptional customer service. Together with our clients, PCE delivers bespoke services and collaborates with project stakeholders from project start to completion, to ensure the best project outcome.
We have advanced expertise and extensive experience in residential/mixed use applications. We believe our following unique would best support your projects:
• | High-/low-rise apartment engineering specialist. Have successfully delivered design of prestigious residential developments.
• | Fully compliant to NSW Engineering Scheme: BDC C9 Mechanical Certifier, DBP Mechanical Design Practitioner
• | Seamless collaborations with Developer, Architects and other consultants to streamline the design process
• | Our tailored solutions are highly cost effective and achieve the best project outcome.
Please refer to the details on our proposed project stage, service scope, and the required key design basis information. We will endeavour to deliver quality, accurate and timely services.
Yours faithfully,
Felix Ye
Director, MEP
M: 0426 076 689
E: felix@pcen.com.au
1 | INTRODUCTION
We have prepared this submission in response to an invitation of from for the provision of our consulting services for 30 Kerr Parade, Auburn.
2 | GENERAL SCOPE OF WORKS
2.1 | Overview
The general scope of our service comprises design development and construction documents stages. We have priced as per the information set provided as detailed in section 2.2 Information provided.
2.2 | Information Provided
We have prepared this submission by using following information:
• | Email sent from Simon Sassine on 7th July 2022, with mech drawings and architectural plans.
• | The project is a boarding house develop and consists of:
- 3 levels of Basement car park consists of 65 car spots.
- 1 Commercial (Restaurant) in Ground Level
- 12 Levels of ensuite rooms from Ground to Level 11.
2.3 | MECHANICAL SERVICES
2.3.1 | Mechanical Services - Extent
| The extent of mechanical service will comprise: | [8 empty] | Mechanical Services - Extent, Group house
• | Car park ventilation system. | [8 empty] | • | Car park ventilation system.
• | Garbage exhaust. | [8 empty] | • | Garbage exhaust.
• | Fire pump room ventilation. | [8 empty] | • | Fire pump room ventilation.
• | Stair pressurization and relief systems. | [8 empty] | • | Air conditioning system design to ensuites.
• | Air conditioning system design to apartments. | [8 empty] | • | Air conditioning system design to other communal area as required.
• | Toilet and laundry ventilation to apartments. | [8 empty] | • | Air conditioning system design to commercial tenancy, warm shell.
• | Rangehood exhaust system to apartments. | [8 empty] | • | Toilet and laundry ventilation to apartments.
• | Outside air system design for noise affected apartments. | [8 empty] | • | Rangehood exhaust system to apartments.
• | Plant room ventilations, including storage rooms, main switch room, grease arrest room, garbage rooms, etc. | [8 empty] | • | Outside air system design for noise affected apartments.
• | Other ventilation to AS 1668.2. | [8 empty] | • | Plant room ventilations, including storage rooms, grease arrest room, garbage rooms, etc.
• | Electrical services associated with mechanical plant and equipment. | [8 empty] | • | Other ventilation to AS 1668.2.
• | Coordinate with architect, electrical, hydraulic fire service and other relevant parties. | [8 empty] | • | Electrical services associated with mechanical plant and equipment.
[10 empty] | • | D&BP Act class 2 building design declaration
2.3.2 | Mechanical Services - Deliverables | [8 empty] | Mechanical Services - Deliverables
| Design Development |  | PDF spatial sketch as required | [6 empty] | Design Development | PDF spatial sketch as required
|  |  | DWG drawings as required | [7 empty] | DWG drawings as required
|  |  | 8 coordination meetings | [7 empty] | 8 coordination meetings
| Construction Documents |  | PDF spatial sketch as required | [6 empty] | Construction Certification | PDF spatial sketch as required
|  |  | Equipment specification | [7 empty] | Equipment specification
|  |  | Full set of drawings in PDF and AutoCAD 2D | [7 empty] | Full set of drawings in PDF and AutoCAD 2D
|  |  | 8 coordination meetings | [7 empty] | 6 coordination meetings
|  |  | D&BP Act class 2 building design declaration | [7 empty] | D&BP Act class 2 building design declaration
| Construction Phase Service |  | Review contractor’s shop drawings | [6 empty] | Construction Phase Service | Review contractor’s shop drawings
|  |  | Answer RFI and site related inquiries | [7 empty] | Answer RFI and site related inquiries
|  |  | Site inspection and defect report, 6 off | [7 empty] | Site inspection and defect report, 6 off
Comissioning witness inspection, 2 off
Provide Asbuilt drawings
2.3.3 | Mechanical Services - Clarifications
| We have not yet allowed for the following in our scope of service and fee. | [8 empty] | Mechanical Services - Exclusion
• | Fire engineering; | [8 empty] | • | Fire engineering;
• | Assessment of compliance with environmental noise regulations; | [8 empty] | • | Assessment of compliance with environmental noise regulations;
• | Preparation of Performance Solutions where Deemed to satisfy requirements of the BCA do not suit the project requirements; | [8 empty] | • | Preparation of Performance Solutions where Deemed to satisfy requirements of the BCA do not suit the project requirements;
• | Refrigeration systems to cool rooms and freezers; | [8 empty] | • | Refrigeration systems to cool rooms and freezers;
• | Revit modelling and documentation. | [8 empty] | • | Assessment of compliance with environmental noise regulations (however, we have the capability for this service and are able to provide an acoustics consultancy fee, if required).
2.4 | CAR PARK VENTILATION CFD SERVICE
Car Park Ventilation CFD scope of services will be as clarified below:
2.4.1 | CFD (Computational Fluid Dynamics) - Extent
• | Car Park Ventilation CFD scope of services will be as clarified below: | [8 empty] | CFD Service - Extent
• | Review of all drawings relevant to the car park design. | [8 empty] | • | Review of all drawings relevant to the car park design.
• | Creation of a three-dimensional model for the car park suitable for the CFD simulations. | [8 empty] | • | Creation of a three-dimensional model for the car park suitable for the CFD simulations.
• | CFD ventilation simulations to assess the performance of the proposed design. This will provide a basis on which to compare subsequent designs. | [8 empty] | • | CFD ventilation simulations to assess the performance of the proposed design. This will provide a basis on which to compare subsequent designs.
• | CFD ventilation simulations for up to three design changes. This includes altering natural ventilation openings, supply/exhaust flow rates, re-locating jet fans, etc. | [8 empty] | • | CFD ventilation simulations for up to three design changes. This includes altering natural ventilation openings, supply/exhaust flow rates, re-locating jet fans, etc.
• | Preparation of a Technical Report detailing the results and recommendations. | [8 empty] | • | Preparation of a Technical Report detailing the results and recommendations.
2.4.2 | Car Park Ventilation CFD - Deliverables | [8 empty] | Car Park Ventilation CFD Deliverables
• | PDF spatial sketch as required | [8 empty] | • | PDF spatial sketch as required
• | Car park CFD ventilation report | [8 empty] | • | Car park CFD ventilation report
• | NSW regulated design and submission | [8 empty] | • | NSW regulated design and submission
• | 1 meeting | [8 empty] | • | 1 meeting
2.4.3 | Car Park Ventilation CFD - Clarifications
We have allowed 3 off model simulation/modification, if additional simulations are required (for example, in the event of still unacceptable CO levels) then these will be discussed with the client and will be subject to a variation.
We have not allowed fire engineering solution for jet fan which might affect sprinkler performance, this will need to be addressed by fire engineer on the job.
3 | PCE Capabilities
3.1 | Expertise
We specialise in providing tailored engineering solutions with a strong focus on high quality, close collaboration, and exceptional customer service. All our consultants are qualified and knowledgeable professionals. We have extensive experience in Mechanical and CFD Performance solution.
3.2 | Qualification
Our team of engineers are highly experienced and fully qualified. Our qualifications relating to this project include:
Felix:
• | MIEAust, M.AIRAH, CPEng, NER, RPEQ | [7 empty] | MIEAust, M.AIRAH, CPEng, NER, RPEQ
• | BDC C9 Mechanical Certifier, DBP Mechanical Design Practitioner | [7 empty] | Master of Engineering in Heating, Gas Supply, Ventilation and Air Conditioning
BDC C9 Mechanical Certifier, DBP Mechanical Design Practitioner
3.3 | Project Experience
| We have enormous experience in this area. Some of our previous works are: | [7 empty] | Project reference sources (auto-generated, do NOT change)
• | 38 Cudgegong Road, Rouse Hill (Zhinar Architects, 295 Apartments, $200m) | [7 empty] | Apartment
• | ‘Crownview’, 373 Crown Street, Wollongong (mixed-used twin tower, 149 apartments)
• | ‘Regent’, 58-68 Regent Street, Kogarah (PBD Architects,12-storey, 96 high-end apartments, $80m)
• | ‘Grand Auburn’, 5-7 Northumberland Road, Auburn (Zhinar Architects, mixed-used, 116 apartment, $110m)
• | 23-27 Schofields Road, Schofields (Binah Construction, 137 Apartments, $100m)
• | 27-33 Ascot Street, Canley Heights (Zhinar Architects, 74 Apartments, $60m)
• | 31 Warriewood Road, Warriewood (DKO Architects, 5-storey 104 apartments, $90m)
• | 35-39 Jenkins Road, Carlingford (Blue Sox Developments, 60 Apartments, $45m)
• | ‘The Pearson’, 2-6 Pearson Ave, Gordon (Wolski Coppin Architecture, boutique apartment)
• | The Mitchell', 11-15 Mitchell Avenue, Jannali (PBD Architects, 31 featured apartments)
3.4 | Project Resources
| Our key personnel proposed for this project are as follows: | [7 empty] | Director/Mechanical Engineer
| Director/Mechanical Engineer |  |  | - Felix Ye (ME CPEng NER RPEQ DBP) |  |  |  |  | - | Felix Ye (ME CPEng NER RPEQ DBP)
We confirm that we will not engage any sub-consultants.
4 | INSURANCE DETAILS
We currently hold the following insurances to as required by authorities
| Insurance type |  | Insurer |  | Amount
| Professional indemnity |  | Allianz |  | 10000000
| Public Liability |  | CGU |  | 20000000
Copies of insurance certificate are available upon request.
5 | CONDITIONS OF ENGAGEMENT
We confirm that this will be a direct commission from your firm. You may accept the offer by completing the Signature of Acceptance form at the end of this document, but if you do not, your continued instructions to us will constitute your acceptance of the offer.
6 | FEE
6.1 | Fee Proposal Details
We are pleased to outline below our lump sum fees for the provision of services to be undertaken in accordance with the aforementioned scope of service.
| Please tick | Services |  |  |  | Amt. ex.GST | Amt. in.GST |  |  | Services |  | Amt. ex.GST | Amt. in.GST
|  | Mechanical-Design Development |  |  |  | 7500 | 8250 |  |  | Mechanical-Design Development |  | 45000 | 49500
|  | Mechanical-Construction Document |  |  |  | 7500 | 8250 |  |  | Mechanical-For Coordination |  | 45000 | 49500
[10 empty] | Mechanical-Construction Document |  | 45000 | 49500
|  | Mechanical Services Total |  |  |  | 15000 | 16500 |  |  | Mechanical Services Total |  | 135000 | 148500
|  | Car Park Ventilation CFD -Kick off |  |  |  | 3000 | 3300
|  | Car Park Ventilation CFD -Final Report |  |  |  | 3000 | 3300
|  | Car Park Ventilation CFD Services Total |  |  |  | 6000 | 6600
6.2 | Hourly Rates
Any additional work required beyond the scope defined will be charged at hourly rates. The following rates (GST exclusive) are current to project completion.
| Project co-ordinator |  | - | 320 | per hour
| Engineer |  | - | 280 | per hour
| Administration |  | - | 150 | per hour
| Site Visit/Meeting(extra) |  | - | 450 | per 3 hour section inclusive travelling
6.3 | Claiming of Fees
Payment is due within 14 days of the date of invoice.
Our fee will be invoiced at the beginning of each design stage.
7 | SIGNATURE AND APPROVAL
RE: 30 Kerr Parade, Auburn
|  | Client |  |  | Engineer
| Company: |  |  |  | Premium Consulting Engineers
| Full Name: |  |  |  | Felix Ye
Director/Mechanical Engineer
NSW Fair Trading C9 Certifier
NSW Fair Trading Professional Engineer
M.E CPEng NER RPEQ
M: 0426 076 689
Signature:
| Date: |  |  |  | 2023-09-19
TERMS AND CONDITIONS
1 | The Consultant shall provide to the Client the consulting services described in the accompanying letter together with such other services as may be agreed from time to time (the "Services").
2 | The Consultant shall provide the Services with such skill, care and diligence as is generally exercised by competent members of the consulting profession performing services of a similar nature, at the time the Services are provided.
3 | The Services will be performed at either or both the site of the project (the "Site") or at other places reasonably required by the Client. Where the locations of the Consultant’s work are not under the Consultant’s control (including the Site), the Client must provide reasonable access to allow the Consultant to fulfil its obligations (including to provide the Services).
4 | The Client shall, at its own cost, as soon as practicable make available to the Consultant all information, documents and other particulars relating to the Client's requirement for the project as is necessary for the Consultant to carry out the services as expressly set out in this Agreement (the "Requirements"). The Consultant is entitled to rely on such information, documents and other particulars as are provided by the Client pursuant to or in connection with this Agreement.
5 | The Client shall pay to the Consultant:
a) the Fee and the Reimbursable Expenses as set out in the accompanying letter together with such other amounts in respect of other services agreed to be provided;
b) reasonable adjustments to the Fee and the Reimbursable Expenses to reflect the additional costs, expenses, liabilities, losses or other amounts incurred or suffered by the Consultant in the performance of the Services and arising out of or in connection with any event or matter beyond the Consultant’s control; and
c) to the extent that amounts payable under this Agreement are not expressed to be GST inclusive, an additional amount for the GST incurred by the Consultant in relation to the supply of the Services ("GST").
6 | The Consultant may claim payment in accordance with the times set out in the accompanying letter or, if no time is set out, monthly in arrears. The Client must pay to the Consultant, without set-off or deduction:
a) the amount payable under this Agreement for the Services provided during the relevant period, within 15 days of the Consultant’s invoice; and
b) the GST payable under this Agreement for the Services provided during the relevant period, within 15 days of receiving a valid tax invoice.
7 | If the Client does not pay the Consultant in accordance with this Agreement then, without prejudice to any other rights or remedies the Consultant may have, interest will be payable from the date of invoice until payment at a rate per annum equal to the Unsecured Personal Overdraft Rate as most recently published by Westpac, plus 1% per annum.
8 | To the maximum extent permitted by law:
a) subject to paragraphs (b), (c) and (d) below, the Consultant’s liability to the Client arising out of or in connection with this Agreement (including the performance or non-performance of the Services), whether under the law of contract, in tort, in equity, under statute or otherwise, shall be limited in aggregate to the amount specified in the accompanying letter or $300,000, if no amount is stated in the letter.
b) the Consultant is not liable to the Client in respect of any indirect, consequential or special losses (including loss of profit, loss of business opportunity and payment of liquidated sums or damages under any other agreement);
c) the Consultant shall be deemed to have been discharged from all liability in respect of the Services whether under contract, in tort, in equity, under statute or otherwise, at the expiration of the period specified in the accompanying letter, or if no date is specified, on the expiration of 3 years from the completion of the Services;
d) if, and to the extent that, any of this clause is void as a result of section 68 of the Trade Practices Act 1974 (Cth), then the Consultant’s liability for a breach of a condition or warranty is limited to:
(i) the supplying of the relevant Services again; or
(ii) the payment of the cost of having the Services supplied again.
9 | Subject to the Client complying with its obligations under the Agreement, the Consultant grants to the Client a non-exclusive, royalty-free and irrevocable licence to use (and allow others to use) any intellectual property (including all drawings, reports, specifications, bills of quantity, calculations and other documents, including "works" as defined in the Copyright Act 1968 (Cth) created or produced by the Consultant) arising out of provision of the Services ("IP Rights") for the purposes of completing the Project. As between the Client and the Consultant, the ownership of the IP Rights vests in the Consultant.
10 | Neither the client nor the Consultant shall disclose to third parties or use for any purpose (other than providing or benefiting from the Services) any information provided by the other unless:
a) required by law;
b) the information is already generally known to the public; or
c) the other consents to the disclosure.
All documentation and materials containing confidential information provided by one party to the other shall be returned upon request.
11 | Any dispute or difference ("Dispute) between the Client and the Consultant may be notified by a party to the other party and the parties shall:
a) firstly meet to negotiate, in good faith, resolution of the Dispute; and
b) secondly, if negotiation fails to achieve a resolution of the Dispute within 5 working days of the notification of the Dispute, attend mediation, administered in accordance with procedures as set out by the Institute of Arbitrators and Mediators Australia, provided that this provision shall not prevent the Consultant from instituting legal action at any time to recover moneys owing by the Client to the Consultant.
12 | The Client may, without prejudice to any other rights or remedies it may have, by written notice served on the Consultant terminate its obligations under this Agreement:
a) if the Consultant is in breach of the terms of the Agreement and the breach has not been remedied within 28 days of a written notice served by the Client on the Consultant specifying the breach and requiring the breach to be remedied; or
b) upon the Client giving the Consultant 60 days' written notice of its intention to do so; or
c) if the Consultant informs the Client that it is insolvent, becomes bankrupt, or becomes subject to any official management, receivership, liquidation, provisional liquidation, voluntary administration, winding up or external administration ("Insolvency Event").
The Consultant may, without prejudice to any other rights or remedies it may have, by notice in writing served on the Client suspend its obligations under this Agreement:
13 | The Consultant may, without prejudice to any other rights or remedies it may have, by notice in writing served on the Client suspend its obligations under this Agreement:
a) immediately by written notice if the Client has failed to pay in accordance with this Agreement; or
b) if the Client is in breach of any of the other terms of the Agreement and the breach has not been remedied within 10 working days (or longer as the Consultant may allow) of a written notice served by the Consultant on the Client specifying the breach and requiring the breach to be remedied.
14 | The Consultant may, without prejudice to any other rights or remedies it may have, terminate its obligations under this Agreement:
a) if the breach referred to in clause 13(a) has not been remedied within 5 days of a written notice served by the Consultant on the Client specifying the breach and requiring the breach to be remedied; or
b) if the Client is in breach of any of the other terms of the Agreement and the breach has not been remedied within 28 days of a written notice served by the Consultant on the Client specifying the breach and requiring the breach to be remedied; or
c) upon the Consultant giving the Client 60 days' written notice of its intention to do so; or
d) if an Insolvency Event occurs in relation to the Client.
15 | If the Consultant considers it appropriate to do so, it may, with the Client's prior approval, which shall not be unreasonably withheld or delayed, engage other consultants to assist the Consultant in specialist areas. The other consultant shall be engaged at the Client's risk, cost and expense, and on its behalf.
16 | Neither party may assign, transfer or sublet any obligations under this Agreement without the written consent of the other. Unless stated in writing to the contrary, no assignment, transfer or subletting shall release the assignor from any obligation under this agreement.
17 | In the interpretation of this Agreement, no rule of construction applies to the disadvantage of one party on the basis that it put forward this Agreement or any part of it.
Note: Subject auto-generated
Note: auto-generated. Type of 'Service' must be input in '01-Project Info' section
Note: Client name, company, project number and date are auto-generated.
Note: Manually input the 'revision'
Note: Chose scope items to suit the project's requirements
Note: manually input project specific building information

## 03b-Drw Transmittal
DOCUMENT TRANSMITTAL
PROJECT NAME | 30 Kerr Parade, Auburn |  |  | PROJECT NUMBER |  |  | 207000C
DOCUMENT DESCRIPTION | Mechanical Drawings |  |  | DISCIPLINE |  |  | Mechanical
TO |  |  |  | ISSUE DATE |  | 2023-09-19
ATT |  |  |  | SENT FROM |  | Felix Ye
Reason for Issue P - Preliminary; T - Tender; C - Construction; I -For Information; A -For approval |  |  |  |  | C
Method of Issue E - Email; P - Post; C - Courier; H - Hand Delivered; U - Upload; M - Media (USB/CD) |  |  |  |  | E
Format of Issue P - PDF; D - DWG; C - PDF & DWG; H - Hard Copy; |  |  |  |  | C
DISCIPLINE |  |  | DATE OF ISSUE
MECHANICAL |  |  | DAY |  | 3
|  |  | MONTH |  | 3
|  |  | YEAR |  | 22
DOCUMENT NAME |  |  | DOC # |  | REVISION
COVER SHEET, DRAWINGS LIST, LEGEND AND NOTES |  |  | M-000 |  | C
SPECIFICATION |  |  | M-001 |  | C
EQUIPMENT SCHEDULES |  |  | M-002 |  | C
DETAILS |  |  | M-003 |  | C
BASEMENT 2 LAYOUT |  |  | M-100 |  | C
BASEMENT 1 LAYOUT |  |  | M-101 |  | C
GROUND FLOOR LAYOUT |  |  | M-200 |  | C
LEVEL 1 LAYOUT |  |  | M-201 |  | C
LEVEL 2 LAYOUT |  |  | M-202 |  | C
LEVEL 3 LAYOUT |  |  | M-203 |  | C
LEVEL 4 LAYOUT |  |  | M-204 |  | C
LEVEL 5 LAYOUT |  |  | M-205 |  | C
LEVEL 6 LAYOUT |  |  | M-206 |  | C
LEVEL 7 LAYOUT |  |  | M-207 |  | C
ROOF LAYOUT |  |  | M-208 |  | C
SCHEMATIC |  |  | M-300 |  | C
Test
Test
DISTRIBUTION LIST
ORGANISATION |  | RECEIVER | NUMBER OF COPIES

## 03a-Design Cert
Mechanical Design Certificate
30 Kerr Parade, Auburn
Pursuant to the provisions of Clause A5.2 of the National Construction Code 2019 Admt 1, Volume 1. | [7 empty] | Pursuant to the provisions of Clause A5G3 of the National Construction Code 2022, Volume 1.
I | Qing Felix Ye |  | of | Premium Consulting Engineers
| (Appropriately qualified person) |  |  | (Firm)
Suite 802, 299 Sussex Street, Sydney NSW 2000
(Address)
Qualifications and experience:
Master of HVAC Engineering, Chartered Professional Engineer (MIEAust No.: 3631369);
NSW Fair Trading C9 Certifier (Reg No.: BDC04672); and
NSW Fair Trading Mechanical Design Practitioner (Reg No.: DEP0000275)
Hereby certify:
That the Mechanical Services Drawings and Specifications have been checked and comply with:
• | The relevant clauses of the National Construction Code 2019 Amendment 1. | [6 empty] | • | The relevant clauses of the National Construction Code 2022.
| BCA Clause |  | Description (Mechanical) | [5 empty] | BCA Clause | Description (Mechanical)
| Specification C1.10(5) |  | Fire Resistance Fire Hazard Property Air-handling ductwork | [5 empty] | Specification 7(S7C5) | Fire Resistance Fire Hazard Property Air-handling ductwork
| C1.10(5) |  | Fire Resistance Fire Hazard Property Air-handling ductwork | [5 empty] | C2D11 | Fire Resistance Fire Hazard Property Air-handling ductwork
| C3.9 |  | Fire Resistance Protection of openings Service penetrations in fire-isolated exits | [5 empty] | C4D10 | Fire Resistance Protection of openings Service penetrations in fire-isolated exits
| C3.12 |  | Fire resistance Protection of Openings Openings in floors and ceilings for services | [5 empty] | C4D13 | Fire resistance Protection of Openings Openings in floors and ceilings for services
| C3.15 |  | Fire resistance Protection of Openings Openings for service installations | [5 empty] | C4D15 | Fire resistance Protection of Openings Openings for service installations
| E2.2 (a), (b)& (c) |  | Smoke Hazard Management General requirements Air Handling Systems | [5 empty] | E2D3 | Smoke Hazard Management General requirements Air Handling Systems
| F4.5 |  | Health and Amenity Light and Ventilation Ventilation of rooms | [5 empty] | F6D6 | Health and Amenity Light and Ventilation Ventilation of rooms
| F4.6 |  | Health and amenity Light and ventilation Natural Ventilation | [5 empty] | F6D7 | Health and amenity Light and ventilation Natural Ventilation
| F4.11 |  | Health and Amenity Light and Ventilation Carparks | [5 empty] | F6D11 | Health and Amenity Light and Ventilation Carparks
| F4.12 |  | Health and Amenity Light and Ventilation Kitchen local exhaust ventilation | [5 empty] | F6D12 | Health and Amenity Light and Ventilation Kitchen local exhaust ventilation
| F6.3 |  | Health and amenity Condensation management Flow rate and discharge of exhaust systems | [5 empty] | F8D4 | Health and amenity Condensation management Flow rate and discharge of exhaust systems
| J3.5 |  | Energy Efficiency Building Sealing Exhaust Fans | [5 empty] | J5D6 | Health and amenity Condensation Management Ventilation of roof spaces
| J5 |  | Energy Efficiency Air-conditioning and Ventilation Systems | [5 empty] | J6 | Energy Efficiency Air-conditioning and Ventilation Systems
[9 empty] | J5 | Energy Efficiency Air-conditioning and Ventilation Systems
• | The referenced Australian Standards listed in the Building Code of Australia (Schedule 4 Referenced Documents) as follows:
| Standard |  | Description (Mechanical) | [5 empty] | Standard | Description (Mechanical)
| AS1668.1:2015 |  | The use of ventilation and airconditioning in Buildings Part 1: Fire and Smoke Control in buildings | [5 empty] | AS1668.1:2015 | The use of ventilation and airconditioning in Buildings Part 1: Fire and Smoke Control in buildings
| AS1668.2:2012 |  | The use of ventilation and air conditioning in buildings Part 2: Mechanical ventilation for acceptable indoor-air quality | [5 empty] | AS1668.2:2012 | The use of ventilation and air conditioning in buildings Part 2: Mechanical ventilation for acceptable indoor-air quality
| AS1668.4:2012 |  | The use of ventilation and air conditioning in buildings Part 4: Natural ventilation of the buildings | [5 empty] | AS1668.4:2012 | The use of ventilation and air conditioning in buildings Part 4: Natural ventilation of the buildings
[9 empty] | AS4674:2004 | Design, construction and fit-out of food premises, Clause 2.5.2
[9 empty] | AS5149.1:2016 | Refrigerating systems and heat pumps - Safety and environmental requirements Part 1: Definitions, classification and selection criteria
[9 empty] | AS5149.2:2016 | Refrigerating systems and heat pumps - Safety and environmental requirements Part 2: Design, construction, testing, marking and documentation
[9 empty] | AS3666.1:2011 | Air-handling and water systems of buildings — Microbial control
• | Fire Engineering Report prepared by BCA Logic (Document No.: 110942-FER-r5)
Performance solution 10 – Basement fire stair pressurisation;
Performance solution 11 – Supermarket smoke hazard management and egress;
Performance solution 13 – Rationalisation of protection of openings facing boundaries;
Performance solution 15 – Rationalisation of stair pressurisation for tower A and Tower B;
Performance solution 16 – Basement jef fans;
• | Carppark Ventilation CFD Assessment prepared by i-Fire (Document No.: 20-087XA77)
The following is a schedule of the relevant service design drawings and specifications.
| Drawing Number |  | Drawing Name |  |  |  | Revision
| M-000 |  | COVER SHEET, DRAWINGS LIST, LEGEND AND NOTES |  |  |  | C
| M-001 |  | SPECIFICATION |  |  |  | C
| M-002 |  | EQUIPMENT SCHEDULES |  |  |  | C
| M-003 |  | DETAILS |  |  |  | C
| M-100 |  | BASEMENT 2 LAYOUT |  |  |  | C
| M-101 |  | BASEMENT 1 LAYOUT |  |  |  | C
| M-200 |  | GROUND FLOOR LAYOUT |  |  |  | C
| M-201 |  | LEVEL 1 LAYOUT |  |  |  | C
| M-202 |  | LEVEL 2 LAYOUT |  |  |  | C
| M-203 |  | LEVEL 3 LAYOUT |  |  |  | C
| M-204 |  | LEVEL 4 LAYOUT |  |  |  | C
| M-205 |  | LEVEL 5 LAYOUT |  |  |  | C
| M-206 |  | LEVEL 6 LAYOUT |  |  |  | C
| M-207 |  | LEVEL 7 LAYOUT |  |  |  | C
| M-208 |  | ROOF LAYOUT |  |  |  | C
| M-300 |  | SCHEMATIC |  |  |  | C
| 0 |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
| 0 | [5 empty] | 0
| 0 |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
| 0 |  | 0 |  |  |  | 0
| 0 | [5 empty] | 0
Yours faithfully,
Name: |  | Qing Ye (Felix) |  |  | Date: | 2023-09-19
Note: drawing list auto-copied from '01-Project Info' section.
Please select the clauses from the following list to suit the porject.
Note: manually input project specific building information

## 03c-Design Compliance Cert
Mechanical Design Compliance Certificate
30 Kerr Parade, Auburn
Pursuant to the provisions of Clause A5.2 of the Building Code of Australia Amendament 1, Volume 1.
I | Qing Felix Ye |  | of | Premium Consulting Engineers
| (Appropriately qualified person) |  |  | (Firm)
Suite 802, 299 Sussex Street, Sydney NSW 2000
(Address)
Qualifications and experience:
Master of HVAC Engineering, Chartered Professional Engineer (MIEAust No.: 3631369);
NSW Fair Trading C9 Certifier (Reg No.: BDC04672); and
NSW Fair Trading Mechanical Design Practitioner (Reg No.: DEP0000275)
Hereby certify:
The Mechanical installation on site to date has to the best of our knowledge and belief, confirmed that the works designed and installed have been in accordance with the requirements of and design intent expressed in the design prepared by Premium Consulting Engineers Pty Ltd.
Subject to effective and thorough implementation of advice issued by Premium Consulting Engineers and to the extent that can reasonably be expected based on our inspections of visible work, we confirm our opinion that the works appear to have been undertaken in accordance with the intent of our documentation.
Yours faithfully,
Name: |  | Qing Ye (Felix) |  |  | Date: | 2023-09-19

## INV-1
TAX INVOICE
Bill to: | [5 empty] | Date: |  | 2022-12-09
[6 empty] | Invoice Number: |  | INV-1
Please quote invoice No. when transferring
[6 empty] | Client Reference: |  | -
|  |  | Description |  |  |  | Amount Ex. GST | Amount In. GST
30 Kerr Parade, Auburn
Mechanical Services
| Payment Instalments |  |  |  | Amount | This pay |  |  |  | Payment Instalments |  | Amount | This pay
Design Development |  |  |  |  | 7500 | 7500 | 7500 | 8250 | Design and Equipment Procurement |  | 30% | 13500 | Paid
Construction Certificate |  |  |  |  | 7500 |  |  |  | System Comissioning |  | 35% | 20000 | Paid
[9 empty] | Project Completion |  | 30% | 13335 | Paid
|  |  |  | Total: | 15000 |  |  |  | Retention |  | 5% | 2500 | 2500
CFD Service
| Payment Instalments |  |  |  | Amount | This pay
CFD Kick-off |  |  |  |  | 3000 | 3000 | 3000 | 3300
CFD Report Final |  |  |  |  | 3000 |  |  |  | Payment method: |  |  | Amount | This pay
[9 empty] | Site visit and investigation: |  |  | 4000 | 4000 | 4000 | 4400
|  |  |  | Total: | 6000 |  |  |  | Tender documentation: |  |  | 3800
[6 empty] | Total | 10500 | 11550
Payment Details:
Bank: | St George Bank |  |  |  |  | Note:
Name: | Premium Consulting Engineers Pty Ltd |  |  |  |  | Payment in 7 days from invoice date
BSB: | 112879
A/C No.: | 415395374 |  |  |  |  | Internal Ref.: | INV-1
|  | Project Type: | Apartment
|  | Service Type: | Mechanical Service
Main Contact:
Note:
If the invoice is copied to external files, MAKE SURE to break data link in the destination file.
Note:
Manually input the invoce amount of this payment instalment
Note:
Total prcicing amount automatically linked in to Fee Proposal 'Fee Table'

## INV-X
TAX INVOICE
Bill to: | [5 empty] | Date: |  | 2023-06-26
[6 empty] | Invoice Number: |  | INV-X
Please quote invoice No. when transferring
[6 empty] | Client Reference: |  | -
|  |  | Description |  |  |  | Amount Ex. GST | Amount In. GST
30 Kerr Parade, Auburn
Mechanical Services
| Payment Instalments |  |  |  | Amount | This pay |  |  |  | Payment Instalments |  | Amount | This pay
Design Development |  |  |  |  | 7500 | Paid | Paid | Paid | Design and Equipment Procurement |  | 30% | 13500 | Paid
Construction Certificate |  |  |  |  | 7500 | 7500 | 7500 | 8250 | System Comissioning |  | 35% | 20000 | Paid
[9 empty] | Project Completion |  | 30% | 13335 | Paid
|  |  |  | Total: | 15000 |  |  |  | Retention |  | 5% | 2500 | 2500
CFD Service
| Payment Instalments |  |  |  | Amount | This pay
CFD Kick-off |  |  |  |  | 3000 | Paid | Paid | Paid
CFD Report Final |  |  |  |  | 3000 | 3000 | 3000 | 3300 | Payment method: |  |  | Amount | This pay
[9 empty] | Site visit and investigation: |  |  | 4000 | 4000 | 4000 | 4400
|  |  |  | Total: | 6000 |  |  |  | Tender documentation: |  |  | 3800
[6 empty] | Total | 10500 | 11550
Payment Details:
Bank: | St George Bank |  |  |  |  | Note:
Name: | Premium Consulting Engineers Pty Ltd |  |  |  |  | Payment in 7 days from invoice date
BSB: | 112879
A/C No.: | 415395374 |  |  |  |  | Internal Ref: | INV-1
|  | Project Type: | Apartment
|  | Service Type: | Mechanical Service
Main Contact:
Note:
If the invoice is copied to external files, MAKE SURE to break data link in the destination file.
To manually fill in the date.
Note:
Manually input the invoce amount of this payment instalment
Note:
Total prcicing amount automatically linked in to Fee Proposal 'Fee Table'

## INV-XX
TAX INVOICE
dd/mm/yyyy
Bill to: | [6 empty] | Date: |  | 00/00/0000
[7 empty] | Invoice Number: |  | INV-XX
Please quote invoice No. when transferring
[7 empty] | Client Reference: |  | -
Break data link
|  |  | Description |  |  |  |  | Amount Ex. GST | Amount In. GST
30 Kerr Parade, Auburn
Mechanical Services
| Payment Instalments |  |  |  |  | Amount | This pay |  |  |  | Payment Instalments |  | Amount | This pay
Design Development | [5 empty] | 0 | 0 | 0 | 0 | Design and Equipment Procurement |  | 30% | 13500 | Paid
Construction Certificate | [5 empty] | 0 |  |  |  | System Comissioning |  | 35% | 20000 | Paid
[10 empty] | Project Completion |  | 30% | 13335 | Paid
[5 empty] | Total: | 0 |  |  |  | Retention |  | 5% | 2500 | 2500
CFD Service
CFD Kick-off | [5 empty] | 0 | 0 | 0 | 0
CFD Report Final | [5 empty] | 0
[5 empty] | Total: | 0 |  |  |  | Payment method: |  |  | Amount | This pay
[10 empty] | Site visit and investigation: |  |  | 4000 | 4000 | 4000 | 4400
[10 empty] | Tender documentation: |  |  | 3800
[7 empty] | Total | 0 | 0
Payment Details:
Bank: | St George Bank | [5 empty] | Note:
Name: | Premium Consulting Engineers Pty Ltd | [5 empty] | Payment in 7 days from invoice date
BSB: | 112879
A/C No.: | 415395374 | [5 empty] | Internal Ref: | INV-1
|  | Project Type: | Apartment
|  | Service Type: | Mechanical Service
Main Contact:
Note:
If the invoice is copied to external files, MAKE SURE to break data link in the destination file.
To manually fill in the date.
Note:
Manually input the invoce amount of this payment instalment
Note:
Total prcicing amount automatically linked in to Fee Proposal 'Fee Table'

## INV-XXX
TAX INVOICE
dd/mm/yyyy
Bill to: | [6 empty] | Date: |  | 00/00/0000
[7 empty] | Invoice Number: |  | INV-XXX
Please quote invoice No. when transferring
[7 empty] | Client Reference: |  | -
Break data link
|  |  | Description |  |  |  |  | Amount Ex. GST | Amount In. GST
30 Kerr Parade, Auburn
Mechanical Services
| Payment Instalments |  |  |  |  | Amount | This pay |  |  |  | Payment Instalments |  | Amount | This pay
Design Development | [5 empty] | 0 | 0 | 0 | 0 | Design and Equipment Procurement |  | 30% | 13500 | Paid
Construction Certificate | [5 empty] | 0 |  |  |  | System Comissioning |  | 35% | 20000 | Paid
[10 empty] | Project Completion |  | 30% | 13335 | Paid
[5 empty] | Total: | 0 |  |  |  | Retention |  | 5% | 2500 | 2500
CFD Service
CFD Kick-off | [5 empty] | 0 | 0 | 0 | 0
CFD Report Final | [5 empty] | 0
[5 empty] | Total: | 0 |  |  |  | Payment method: |  |  | Amount | This pay
[10 empty] | Site visit and investigation: |  |  | 4000 | 4000 | 4000 | 4400
[10 empty] | Tender documentation: |  |  | 3800
[7 empty] | Total | 0 | 0
Payment Details:
Bank: | St George Bank | [5 empty] | Note:
Name: | Premium Consulting Engineers Pty Ltd | [5 empty] | Payment in 7 days from invoice date
BSB: | 112879
A/C No.: | 415395374 | [5 empty] | Internal Ref: | INV-1
|  | Project Type: | Apartment
|  | Service Type: | Mechanical Service
Main Contact:
Note:
If the invoice is copied to external files, MAKE SURE to break data link in the destination file.
To manually fill in the date.
Note:
Manually input the invoce amount of this payment instalment
Note:
Total prcicing amount automatically linked in to Fee Proposal 'Fee Table'

## DBP
Design and Building Practitioners Act Regulated Design Documents
F- Class of design: Mechanical (prepared by a registered design practitioner in the class of mechanical engineering)
| Design category | Design aspects and details | Minimum requirements for design category | Min scale
F-1 | Services Masterplans | - Routes of pipework, pits and cabling on the site - Identify those services that are unable to be concealed - All distribution methods and arrangements for Utilities required for compliance with the BCA - Controls to essential maintenance systems (EMS) items, including fire and life safety and mechanical. |  | 1:500
F-2 | Mechanical Ventilation Plans | Details demonstrating compliance with mechanical ventilation in accordance with F4.5, F4.11 and F4.12 - Heating Ventilation and Air Conditioning (HVAC) plans for all systems, including: - Bathroom, laundry and rangehood exhaust and make-up air solutions - Outdoor air ventilation solutions - Corridor and lobby ventilation solutions - Car park ventilation solutions - Plant and utility room ventilation solutions - Any commercial kitchen ventilation provisions for associated retail spaces - Ducted and non-ducted air conditioning systems - Filtration provisions, including the requirements of AS 1668.2 and the NSW Public Health Regulation - Refrigerant, heating water and chilled water pipework systems serving the air conditioning, including details of all insulation requirements; - Coordinated condensate drainage provisions; - Coordinated intake, exhaust and make-up openings through the façade - Provisions for maintenance access, balancing and commissioning - Coordinated details and finishes of non-mechanical building elements used as shafts and plenums to convey air; - Occupant control interfaces. - Schematic representation of air-side, water-side and refrigeration systems, (but only) where necessary to convey the requirements of the design; - any provisions for supplementary tenancy services, including future board/meeting rooms heat loads and air pressurisation systems; - Scaled elevations, sections and details where necessary to convey the requirements of the design - Mechanical services switchboard schedules, single line diagrams and interfaces for coordination - Heating water and chilled water layouts, equipment and infrastructure, including: - chilled water pipes supply and return from plant rooms to relevant floor take-offs - domestic hot water generation (if not provided under the plumbing trade) - Details of equipment supports, including seismic restraints required by AS 1170.4 - Functional Control Description Operating instructions for occupants, including identification of design assumptions and expectations relating to their use of the space. | Design must be suitable for construction. | 1:100
G- Class of design: Mechanical (prepared by a registered design practitioner in the class of mechanical engineering or fire systems - mechanical smoke control)
| Design category | Design aspects and details | Minimum requirements for design category | Min scale
G-1 | Fire and Smoke Control Systems (Mechanical Services) | * Methods of protecting penetrations in elements required to have an FRL, including fire dampers, subducts and enclosed ductwork construction, all coordinated with associated trades * Details of all smoke hazard management systems in accordance with E2, including all required fire and smoke control systems in accordance BCA Specifications and AS 1668.1 including: - Stair pressurisation and relief - Shutdown systems - Miscellaneous ventilation systems - Carpark ventilation control - Any commercial kitchen ventilation provisions for associated retail spaces - Coordinated interfaces with fire safety design including a Fire Matrix * Details of all fire and smoke control systems required by a Performance Solution applicable to the development * Baseline Data design documentation in accordance with AS 1668.1 | Design must be suitable for construction. | 1:100

## RFI
Fee Proposal Stage
| Items | Description | Client Reply | PCE Comments
Documents
DA Conditions
Stamped Architecture Drawings
Latest Architecture Drawings
FEBQ/Fire Engineering Report
| Acoustic Report (if exists) | Whether natural ventilation of the apartments has been affected by Road noise
BASIX Report
BCA Report
Existing mechanical drawings (if exist)
Questions |  |  |  |  | Refer Superior Air Conditioning projectS
What is the the BCA Class of the building?
Is the building Effective Height more than 25m?
Doe the development have any specific requirements such as budget, timeline, marketing etc?
Preliminary Design Stage
| Items | Remarks | Client Reply | PCE Comments
Documents
Project contact list
Project program (if available)
Updated Architecture Drawings (.DWG & .PDF)
Site survey drawings indicating site levels
Latest FEBQ/Fire Engineering Report
Latest BCA Report
| Latest Acoustic Report | Final BASIX Report
Latest BASIX Report
Existing mechanical drawings (if exist)
Design Intention Questions
Commom Area
| Has any DTS design been done for the Car park? | DTS Design
| Has a carpark ventilcation CFD (computational fluid dynamics) performance solution been developed? If yes, can you please provide a copy of Car Park Ventilation CFD Report? | PCE is specilaist of carpark CFD study and offer optional CFD study service which can achieve best financial and perdformance outcome for the project.
From achtectural design perspective, is it possible the Fire control room be naturally ventilated?
Can you please provide Fire Pump plantroom details and fire pump model?
Can you please provide/clarify the location of main switchroom?
| Have any Fire Engineering study been done about Ground/Lower Level Zone Pressurization | Performance solution via FER to take out?
Will the basement carpark's entrance be open to atmosphere at all time, or be closed by motorised gate?
Apartment
| Any preference on the type/mounting arrangement of the airconditoning units in apartment, such as: -Single wall mounted -Multiple wall mounted -Split ducted (with day night mode) - Mini VRF Bulkhead Type - Centralized VRF | Single Wall Mounted Split
| From architecrual perspective, do you have any preference on the location of airconditoning condensor units,, such as: - Centralised plant area on ground floor (outdoor) - Centralised plant aree on roof - Centralised plant area in basement carpark - Decentralised on each apartment's balcony Please specify if you have other considerations | Multiple Wall Mounted Split Split Ducted with Day/Night Mode Mini VRF Bulkhead Type Centralized VRF Condenser Location, Balcony or Centralized Plant Other, to specify
| From interior design perspective, do you have any preference on apartment wet area(toilet, kitchen etc) ceiling arrangement, such as: - Sheetmetal duct normal size with bulkhead ceiling - Flatpack travel in 2700 ceiling, discharge via nib wall - Flatpack travel in 2700 ceiling, discharge via sliding door subhead Please specify if you have other considerations | Sheetmetal duct normal size with bulkhead ceiling Flatpack travel in 2700 ceiling, discharge via nib wall Flatpack travel in 2700 ceiling, discharge via sliding door subhead
Do you have any preference on the apartment's wet area ventilation, such as the following options: - Centralized toilet exhaust fan - Individual Inline Fan
| Does the client have any preference on type of arpartment unit's mechanical ventilation,such as the following options: - Separate switch/interlocked with FCU - Individual Supply to Living Area and Bedrooms - Supply to the Back of FCU | Separate switch/interlocked with FCU Individual Supply to Living Area and Bedrooms Supply to the Back of FCU
Slab fold, transfer slab details?
Perimeter setdown for balcony?

## RFI1
30 Kerr Parade, Auburn
Mechanical Service
Request for Information
RFI # | Location | Details | Level of Importance | Status | Request | Response | Notes | Response
[5 empty] | Date | Date
RFI -01 | B1 Chiller and Coiler Plant | Can not find the location of the tap in point in basement for Morrison hotel CHW and HHW, how much cooling and heating capacity we can get? | High | Open | 2023-02-03
RFI-02 | B4 Wellness Centre | Please provide architecuture drawings for B4 wellness centre for AC load calculation | High | Open | 2023-02-03
RFI-03 | Ground AHU Plant Room | As per the air schemtic from KEY 00088-M300, AHU-FC-2 has total 2440L/s supply air, 1840L/s to Ground Level and 600 L/s to Upper ground level, In order to put AHU-FC-2 back to base building, do we need to blank off the 600 L/s supply to Upper ground level? | Medium | Open | 2023-02-03
RFI-04 | Heating Source | Please clarify whether we can use a thermal meter to let all food court AHU to connect to base building low pressure heating hot water system. | Medium | Open | 2023-02-03

## Ver.
Revision | Date | Created by | Reviewed by | Description
0.1 | 2022-06-18 | Freeman |  | Initial draft as per workshop 11//6/2022 - 01-Project info updated - 02a- Fee Calc added -02b - Fee proposal updated per 'MS Word' versioned resi fee proposal -03a - Transmital added -03b- Design Certififacte updated by adding project BoD documents -03c-Design Complaince Certicate added
0.2
0.3 | 2022-07-20 | Felix Y |  | Invoice status summary added in 'Project Info'
0.4 | 2022-07-22 | Freeman J |  | - Logo and contact details in Header changed - 4 invoice sheets created and linked to 'Project Info' invoice status summary - Client first name field removed from 'Project Info' - Transmittal client details linked to 'Project Info'
0.4 | 2022-08-06 | Freeman J |  | - Service Type and Project Type added in "Project Info' and linked to 'Invoice' Tab - Invoice layout and format standardized
0.5 | Not recorded | Felix Y
0.6 | 2022-11-08 | Freeman J |  | - 'proposal' cover page date format consitent to 'invoice' - 'proposal' extra lines for service scope and exclusions - 'project info' project type and service type adjusted - 'Fee Proposal' introduction description, incorrect link of service stype corrected
0.7 | 2022-11-21 | Freeman J |  | - '01-Project Info' added project reference list for Group House, Apartment, Mix-used Complex - 'Invoice' tab service type combing 4 services in one text -'01-Project Info' Project refence list, extra lines added (only first 10 projects will be added to Projecr Reference in Fee Proposal)
0.9 | 2023-07-03 | Felix Y |  | - Update a lot of bugs in the using process - Updated cell name by Mario for automation

## Car park ventilation cost analy
Building A Car park Ventilation Cost Analysis - Estimation
| Deem-to-Satisfy | Performance solution | Note
Exhaust Air flow Change | 24000L/s | 17000L/s | 30% reduction
Supply Air flow Change | 20400L/s | 14450L/s | 30% reduction
CFD report cost | 0 | 8000
Fan Cost, Ex GST | 15000 | 14000
Variable Speed Drive Cost, Ex GST | 5000 | 5000
Ductwork and fitting Cost, Ex GST | 48000 | 24000 | Consider conservative of 50% ducwork saving
Grille Cost, Ex GST | 12000 | 6000 | Consider conservative of 50% grille saving
Installation and Commissioning Cost, Ex GST | 48000 | 34000
Wiring and Control Cost, Ex GST | 12000 | 9000
In Total, Ex GST | 140000 | 100000 | Cost saving $50000, Cost reduces by 29%
Building B and Health Service Car park Ventilation Cost Analysis - Estimation
| Deem-to-Satisfy | Performance solution | Note
Exhaust Air flow Change | 30000L/s | 22500L/s | 25% reduction
Supply Air flow Change | 25500L/s | 19100L/s | 25% reduction
CFD report cost | 0 | 8000
Fan Cost, Ex GST | 22000 | 19000
Variable Speed Drive Cost, Ex GST | 5000 | 5000
Ductwork and fitting Cost, Ex GST | 58000 | 29000 | Consider conservative of 50% ducwork saving
Grille Cost, Ex GST | 15000 | 7500 | Consider conservative of 50% grille saving
Installation and Commissioning Cost, Ex GST | 52000 | 38000
Wiring and Control Cost, Ex GST | 12000 | 9000
In Total, Ex GST | 164000 | 115500 | Cost saving $48500, Cost reduces by 30%
Hi Laurence,
See the attached our fee proposal for your review and approval.
Please be advised that we have included Car Park Computational Fluid Dynamics (CFD) analysis. This flagship service, provided by our in-house team at PCE, represents a tailored solution to facilitate the coordination within confined basement areas. Moreover, it achieves a substantial reduction, approximately 20-30%, in the flow rate of the ventilation system within the car park while simultaneously minimizing the extent of horizontal ductwork.
For your reference, we have attached a sample report and compiled a high-level cost analysis to provide you with a preliminary understanding of the project's financial implications.

## Mechanical Design CertificateX (hidden)
Mechanical Design Certificate
PROJECT: |  | 30 Kerr Parade, Auburn
2023-09-19
Pursuant to the provisions of Clause A2.2 of the Building Code of Australia, Volume 1.
I | Qing Felix Ye |  |  | of | Premium Consulting Engineers
| (Appropriately qualified person) |  |  |  | (Firm)
G02/22 Aitchison Street, St Lenarods NSW 2065
(Address)
Qualifications and experience:
Master of HVAC Engineering
Chartered Professional Engineer (MIEAust No.: 3631369)
hereby certify:-
That the Mechanical Services Drawings and Specifications have been checked and comply with:
• | The relevant clauses of the Building Code of Australia 2019.
| BCA Clause |  | Description (Mechanical)
| E2.2 (b)&(c) |  | Smoke Hazard Management General requirements Air Handling Systems
| F4.5 |  | Health and Amenity Light and Ventilation Ventilation of rooms
| F4.12 |  | Health and Amenity Light and Ventilation Kitchen local exhaust ventilation
| J5 |  | Energy Efficiency Air-conditioning and Ventilation Systems
• The referenced Australian Standards listed in the Building Code of Australia (Specification A1.3) as follows:
| Standard |  | Description (Mechanical)
| AS 1668.1:2015 |  | The use of ventilation and airconditioning in Buildings; Part 1 Fire and Smoke Control in buildings
| AS 1668.2:2012 |  | The use of ventilation and air conditioning in buildings; Part 2 Mechanical ventilation for acceptable indoor-air quality
| AS 3000 |  | SAA Wiring Rules
| AS 4254.1&2:2012 |  | Ductwork for air handling systems in buildings.
The following is a schedule of the relevant service design drawings and specifications.
• | Drawings:
| Drawing No. |  |  |  | Reversion
| M-00 |  |  |  | A
| M-01 |  |  |  | A
Qing Felix Ye Mechanical Engineer Mobile: 0426 076 689
Premium Consulting Engineers Pty Ltd
A: Suite G02, 22-24 Atchison St, St Leonards, NSW 2065
P: 0426 076 689
E: felix@pcen.com.au

## Mechanical Fee ProposalXXX (hidden)
www.pcen.com.au
A: Suite 802, 299 Sussex Street
Sydney, NSW 2000
P: 0426 076 689
E: admin@pcen.com.au
Attention: | Sarah
No.8 Canteen
Dear | Sarah
Pursuant to the provisions of Clause A2.2 of the Building Code of Australia, Volume 1.
| I | Qing Felix Ye | of | Premium Consulting Engineers
|  | (Appropriately qualified person) |  | (Firm)
Suite 802, 299 Sussex Street, Sydney NSW 2000
(Address)
Qualifications and experience:
Master of HVAC Engineering, Chartered Professional Engineer (MIEAust No.: 3631369)
NSW Fair Trading C9 Certifier (Reg No.: BDC04672) And
NSW Fair Trading Professional Engineer (Reg No.: PRE0000255)
Hereby certify:
That the Mechanical Services Drawings and Specifications have been checked and comply with:
• | The relevant clauses of the National Construction Code of Australia 2019 Amendment 1.
| BCA Clause | Description (Mechanical)
| E2.2 (b)&(c) | Smoke Hazard Management General requirements Air Handling Systems
| F4.5 | Health and Amenity Light and Ventilation Ventilation of rooms
| F4.12 | Health and Amenity Light and Ventilation Kitchen local exhaust ventilation
| J5 | Energy Efficiency Air-conditioning and Ventilation Systems
[5 empty] | • | Complance Development ???
[5 empty] | • | DA condition
www.pcen.com.au
A: Suite 802, 299 Sussex Street
Sydney, NSW 2000
P: 0426 076 689
E: admin@pcen.com.au
• | The referenced Australian Standards listed in the Building Code of Australia (Specification A1.3) as follows:
| Standard | Description (Mechanical)
| AS1668.1:2015 | The use of ventilation and airconditioning in Buildings Part 1: Fire and Smoke Control in buildings
| AS1668.2:2012 | The use of ventilation and air conditioning in buildings Part 2: Mechanical ventilation for acceptable indoor-air quality
| AS1668.4:2012 | The use of ventilation and air conditioning in buildings Part 4: Natural ventilation of the buildings
| AS5149.1:2016 | Refrigerating systems and heat pumps - Safety and environmental requirements Part 1: Definitions, classification and selection criteria
| AS5149.2:2016 | Refrigerating systems and heat pumps - Safety and environmental requirements Part 2: Design, construction, testing, marking and documentation
The following is a schedule of the relevant service design drawings and specifications.
| Drawing No. | Reversion
| M-00 | A
| M-01 | A
| M-02 | A
Yours faithfully,
Name: | Qing Ye (Felix) |  | Date: | 2023-09-19

## Mechanical Fee Proposalx (hidden)
www.pcen.com.au
A: Suite 802, 299 Sussex Street
Sydney, NSW 2000
P: 0426 076 689
E: admin@pcen.com.au
Attention: | Sarah
No.8 Canteen
Dear | Sarah
Thank you for the opportunity to submit this fee proposal for the Mechanical service for the above project.
I | Qing Felix Ye |  | of | Premium Consulting Engineers
| (Appropriately qualified person) |  |  | (Firm)
Suite 802, 299 Sussex Street, Sydney NSW 2000
(Address)
Qualifications and experience:
Master of HVAC Engineering, Chartered Professional Engineer (MIEAust No.: 3631369)
NSW Fair Trading C9 Certifier (Reg No.: BDC04672) And
NSW Fair Trading Professional Engineer (Reg No.: PRE0000255)
Hereby certify:
That the Mechanical Services Drawings and Specifications have been checked and comply with:
• | The relevant clauses of the National Construction Code of Australia 2019 Amendment 1.
| BCA Clause | Description (Mechanical)
| E2.2 (b)&(c) | Smoke Hazard Management General requirements Air Handling Systems
| F4.5 | Health and Amenity Light and Ventilation Ventilation of rooms
| F4.12 | Health and Amenity Light and Ventilation Kitchen local exhaust ventilation
| J5 | Energy Efficiency Air-conditioning and Ventilation Systems
www.pcen.com.au
A: Suite 802, 299 Sussex Street
Sydney, NSW 2000
P: 0426 076 689
E: admin@pcen.com.au
• | The referenced Australian Standards listed in the Building Code of Australia (Specification A1.3) as follows:
| Standard | Description (Mechanical)
| AS1668.1:2015 | The use of ventilation and airconditioning in Buildings Part 1: Fire and Smoke Control in buildings
| AS1668.2:2012 | The use of ventilation and air conditioning in buildings Part 2: Mechanical ventilation for acceptable indoor-air quality
| AS1668.4:2012 | The use of ventilation and air conditioning in buildings Part 4: Natural ventilation of the buildings
| AS5149.1:2016 | Refrigerating systems and heat pumps - Safety and environmental requirements Part 1: Definitions, classification and selection criteria
| AS5149.2:2016 | Refrigerating systems and heat pumps - Safety and environmental requirements Part 2: Design, construction, testing, marking and documentation
The following is a schedule of the relevant service design drawings and specifications.
| Drawing No. | Reversion
| M-00 | A
| M-01 | A
| M-02 | A
Yours faithfully,
Name: | Qing Ye (Felix) |  |  | Date: | 2023-09-19

## Mechanical Fe Proposal (hidden)
2023-09-19
Attention: | #REF!
0
Dear xx,
| RE: | 30 KERR PARADE, AUBURN
Thank you for the opportunity to submit this fee proposal for the Mechanical service for the above project.
1. | GENERAL
1.1 | Out of Project Scope
| • | Describe the engineering systems by means of drawings.
| • | Carry out detailed calculations.
| • | Pre-empt and address constructability issues within documents where possible.
| • | Refer details for client and authority approval where appropriate.
| • | Co-ordination checks with other services.
2. | SCOPE OF WORK
2.1 | Mechanical Services- Extent
The extent of mechanical services document comprises:
| • | Map out existing mechanical components;
| • | Commercial kitchen exhaust and makeup air system design;
| • | Air conditioning design to the tenancy area as required;
| • | Natural ventilation design;
| • | Other ventilation as required to AS 1668.2.
2.2 | Deliverables
| • | Full set of mechanical drawings;
| • | Mechanical design certificate;
| • | Equipment selection;
3. | CONDITIONS OF ENGAGEMENT
We confirm that this will be a direct commission from your firm.
You may accept the offer by completing the Signature of Acceptance form at the end of this document, but if you do not, your continued instructions to us will constitute your acceptance of the offer.
4. | KEY PERSONNEL
Our key personnel proposed for this project are as follows:
|  | Director/Mechanical Engineer |  |  |  | - | Felix Ye
We confirm that we will not engage any sub-consultants.
5. | FEE
5.1 | Fee Proposal Details
We are pleased to outline below our lump sum fees for the provision of services to be undertaken in accordance with the aforementioned scope of service.
|  |  | Documentation |  | TOTAL(ex. GST) | TOTAL(Inc.GST)
Mechanical
Any additional work required beyond the scope defined will be charged at hourly rates. The following rates (GST exclusive) are current to project completion.
| Engineer |  |  | $ 150 per hour $ 350 per each (extra)
Site Visit
Please do not hesitate to contact us if you have any queries or if any of the above is at variance with your understanding of our scope for this project. Yours faithfully, Felix Ye Director Mechanical Engineer CPEng No.: 3631369 Mobile: 0426 076 689

## Mechanical Fee Proposal (2) (hidden)
2023-09-19
Attention: | #REF!
0
Dear xx,
| RE: | 30 KERR PARADE, AUBURN
Thank you for the opportunity to submit this fee proposal for the Mechanical service for the above project.
1. | GENERAL
1.1 | Out of Project Scope
| • | Describe the engineering systems by means of drawings.
| • | Carry out detailed calculations.
| • | Pre-empt and address constructability issues within documents where possible.
| • | Refer details for client and authority approval where appropriate.
| • | Co-ordination checks with other services.
2. | SCOPE OF WORK
2.1 | Mechanical Services- Extent
The extent of mechanical services document comprises:
| • | Map out existing mechanical components;
| • | Commercial kitchen exhaust and makeup air system design;
| • | Air conditioning design to the tenancy area as required;
| • | Natural ventilation design;
| • | Other ventilation as required to AS 1668.2.
2.2 | Deliverables
| • | Full set of mechanical drawings;
| • | Mechanical design certificate;
| • | Equipment selection;
3. | CONDITIONS OF ENGAGEMENT
We confirm that this will be a direct commission from your firm.
You may accept the offer by completing the Signature of Acceptance form at the end of this document, but if you do not, your continued instructions to us will constitute your acceptance of the offer.
4. | KEY PERSONNEL
Our key personnel proposed for this project are as follows:
|  | Director/Mechanical Engineer |  |  |  | - | Felix Ye
We confirm that we will not engage any sub-consultants.
5. | FEE
5.1 | Fee Proposal Details
We are pleased to outline below our lump sum fees for the provision of services to be undertaken in accordance with the aforementioned scope of service.
|  |  | Documentation |  | TOTAL(ex. GST) | TOTAL(Inc.GST)
Mechanical
Any additional work required beyond the scope defined will be charged at hourly rates. The following rates (GST exclusive) are current to project completion.
| Engineer |  |  | $ 150 per hour $ 350 per each (extra)
Site Visit
Please do not hesitate to contact us if you have any queries or if any of the above is at variance with your understanding of our scope for this project. Yours faithfully, Felix Ye Director Mechanical Engineer CPEng No.: 3631369 Mobile: 0426 076 689